## How to use
Inspection and test plan (ITP) — how to use it
Guide and the rules behind it: https://worgify.com/resources/templates/inspection-test-plan/
One line per inspection or test, in the order they happen on the job. For each one: the document it follows, the acceptance criteria, the record it produces, how often, and what each party does.
The sheet holds a complete example for a welded steel structure in EXC2 (EN 1090-2). Keep the steps that apply, change the rest, and add your record numbers as the job goes.
Intervention codes
P – perform | The party that does the activity and keeps the record (usually the manufacturer).
H – hold point | Work stops at this step until the named party has inspected or reviewed it and released it. No release, no next step.
W – witness point | The named party is notified in time and may attend. If they don't come within the agreed notice, work goes on and the record says so.
R – review | The party reviews the records (reports, certificates) without attending.
M – monitor | The party may spot-check the activity at any time, without notice.
The columns
Step, Phase, Activity | Number the steps and keep them in the order of the work. Say what is checked, not just the name of the operation.
Reference document | The procedure, drawing or standard the activity follows.
Acceptance criteria | The level, not only the standard: 'EN ISO 5817 level C', not 'EN ISO 5817'. A line without criteria is a schedule, not an inspection.
Record | The document the step produces. If there is no record, nobody can show later that it happened.
Frequency / extent | Each part, each joint, 10% of welds, each lot, once per job.
Manufacturer, Client, Third party | One code each, from the list.
Record no., Released by / date | Filled in during the job: the report or record number, and who released the step and when (essential for H points).
Before you send it to the client
Notice | Agree how much notice H and W points need and how it is given; write it in the header.
Revision | Change the revision whenever the plan changes, and have the client approve each revision.
Free template by Worgify — worgify.com

## ITP
Inspection and test plan (ITP) | [10 empty] | Free template by Worgify — worgify.com
| Job no. | 2611 (example) | Client | Example client | Structure / item | Steel frame, warehouse extension
| ITP no. / rev. | ITP-2611 rev. 0 | Execution class | EXC2 | Standards | EN 1090-2, EN ISO 3834-3
| Prepared by | A. Clarke, welding coordinator | Approved by (client) |  | Notice for H and W points | 2 working days, by email
P perform (does the activity, keeps the record) · H hold point (work stops until the party releases it) · W witness point (party notified, work goes on if they don't attend) · R review of records · M monitor (spot checks, no notice) · – no intervention
Example for a welded steel structure in EXC2 (EN 1090-2). Keep what applies to your job, change the rest, and get the client to approve the revision.
Step | Phase | Activity / what is checked | Reference document | Acceptance criteria | Record | Frequency / extent | Manufacturer | Client | Third party | Record no. (during the job) | Released by / date
1 | Before production | Contract review: execution specification complete (EXC, quality level, NDT extent, tolerance class, surface treatment) | Contract, execution specification, EN 1090-2 clause 4 | All requirements identified and agreed; open points closed in writing | Contract review record | Once per job | P | R | –
2 | Before production | Welding documents: WPS and supporting WPQR, welder certificates, welding coordinator | EN ISO 15609-1, EN ISO 15614-1, EN ISO 9606-1, EN ISO 14731 | Each WPS covered by a WPQR; welders qualified for the ranges, six-monthly confirmations up to date | WPS/WPQR list, welder list with certificates | Once, and for each new WPS or welder | H | R | R
3 | Materials | Receipt of steel: inspection certificate against the order, heat number on the material matches the certificate, visual and dimensional check | EN 10204, EN 10025-2, purchase order, EN 1090-2 clause 5 | EN 10204 type 3.1 certificate; grade S355J2+N, dimensions and chemistry/mechanical values within EN 10025-2 | Receiving inspection record + 3.1 certificates | Each delivery | P | R | R
4 | Materials | Receipt of welding consumables: designation, batch, certificate, storage | EN ISO 14341, WPS, manufacturer's data | Designation as on the WPS; inspection document received; stored dry as the maker requires | Receiving record | Each batch | P | – | M
5 | Fabrication | Cutting and marking: piece mark and heat number transferred to every part before cutting; cut quality | Cutting lists, EN 1090-2 clause 6, EN ISO 9013 | Every part marked and traceable to its heat; cut surface within the EN 1090-2 requirements | Cutting list with heat numbers | Each part | P | M | –
6 | Fabrication | Fit-up before welding: joint preparation, root gap, alignment, tack welds | Drawings, WPS, EN ISO 9692-1 | Preparation and gap within the WPS; misalignment within the drawing tolerances | Fit-up check in the weld log | Each joint (first-off witnessed) | P | W | –
7 | Welding | Welding to the approved WPS by a qualified welder; preheat and interpass temperatures checked; welder ID recorded for each joint | WPS, EN 1090-2 clause 7, EN ISO 9606-1, weld map | Parameters within the WPS; welder qualified for the joint; preheat not below the WPS minimum | Weld map and weld log | Continuous | P | M | M
8 | Inspection | Visual testing (VT) of the welds | EN ISO 17637, EN 1090-2 clause 12 | EN ISO 5817 quality level C (EN 1090-2 for EXC2) | VT report (inspector competence as the specification requires) | 100% of welds | P | R | R
9 | Inspection | Supplementary NDT: MT on fillet and partial-penetration welds, UT on full-penetration butt welds | EN ISO 17638 (MT), EN ISO 17640 (UT), EN 1090-2 clause 12 | MT: EN ISO 23278; UT: EN ISO 11666, the levels that correspond to EN ISO 5817 level C (EN ISO 17635) | MT and UT reports, NDT operator level 2 to EN ISO 9712 | Extent EN 1090-2 sets for EXC2, by weld type and utilisation (e.g. 10% of transverse butt welds in tension) | P | W | R
10 | Inspection | Repair of rejected welds and re-inspection | Nonconformity procedure, WPS | As for the original weld; repair recorded on the weld map (R1, R2…) | NCR, repeat NDT report | Each repair | P | R | R
11 | Inspection | Dimensional check of each assembly | Drawings, EN 1090-2 clause 11 | Essential tolerances of EN 1090-2; functional tolerances, class 1 unless the specification says otherwise | Dimensional report | Each assembly (first-off witnessed) | P | W | –
12 | Inspection | Release for surface treatment: all VT, NDT and dimensional results accepted, nonconformities closed | This ITP | All records of steps 7 to 11 complete and accepted | Release signed on this ITP | Each lot | H | H | R
13 | Surface treatment | Surface preparation and coating: blast cleaning, weld and edge preparation, dry film thickness | Coating specification, EN 1090-2 clause 10, EN ISO 8501-1, EN ISO 8501-3, ISO 19840 | Sa 2½; preparation grade P2 (or as specified); dry film thickness as the coating specification | Coating inspection report | Each lot | P | W | R
14 | Delivery | Final inspection: marking, completeness, CE marking and declaration of performance | EN 1090-1, drawings, packing list | All steps closed; parts marked as drawn; CE marking and DoP issued | Final inspection record, DoP | Each delivery | P | H | R
15 | Delivery | Quality dossier: certificates, WPS/WPQR, welder certificates, weld map and log, VT/NDT reports, dimensional and coating reports, NCRs, DoP | Contract, EN 1090-2 clause 4 | Complete and traceable to each assembly | Dossier with index | Once per job | P | R | R

## Lists
Intervention code
P
H
W
R
M
–
Add your own values under a list: the drop-downs read the cells shown in each list's range.